## Slide 1
24 October 2018
ST1 Maintenance & Modernization Summit
Amphib Summit: E2E Process Review & Avail Analysis
Presented by:
CAPT Steve Murray
Surface Ship Readiness and Sustainment (PMS 443)
CAPT Andy Johnson
Surface Maintenance Engineering Planning Program (SURFMEPP)

## Slide 2: Objectives & Process
Objective
Evaluate stakeholder performance in Advanced Planning, Planning, Integration and Execution to identify, document and trend processes inconsistent with successful ship availability execution
Process
O-6 level meeting held 20-21 Sep with representatives from SEA 21, CNRMC, SEA 05, RMCs, TYCOM, ESG, PEO, NAVSUP, MARFORCOM, FFC, INSURV and SPAWAR
Analysis and briefings provided by SURFMEPP, PMS 443, SWRMC, MARMC, CNRMC and INSURV
Review availabilities to identify root causes for avail extensions
  USS BATAAN (LHD 5)
  USS CARTER HALL (LSD 50)
  USS AMERICA (LHA 6)
  USS BOXER (LHD 4)
  USS SOMERSET (LPD 25)
Develop actionable recommendations to improve performance
Stakeholders teaming to improve Amphibious Ship availability

## Slide 3: Amphibious Ship Findings
No Amphibious Ship Availability specific items were noted
  Diesel parts are an Amphib specific issue but other ship classes also have LLTM challenges
Planning, Long Lead Time Material (LLTM), Execution, and Growth/New work identified as key challenge areas during avail analysis:
  Planning with poor knowledge of CSMP (scope and accuracy)
  Government late addition of new work
  No clear material procurement process owner
  Contracting strategy and Change management (RCC, UPOBS, etc)
    PSI/PSO initiatives addressing
Identifying Root Causes Preventing On-Time Delivery

## Slide 4: ST1 ESC Leading Actions
Actions:
  Accomplish assessments on the right equipment at the right time
    ESC Champion: CAPT Dowd (CNSL N43)/CDR Karosich (CNSP N43)
  Develop a Bilge Phasing Plan (similar to tanks) to level load bilge work
    ESC Champion: CAPT Johnson (CO SURFMEPP)
  Improve material process (ordering, inventory, delivery)
    ESC Champion: Dale Hirschman (CNRMC C200)
  Improve feedback loop for Avail Duration Scorecard (ADS)
    ESC Champion: CAPT Byrne (PMS 407)
Actionable Solutions For Immediate Impact To Future Avails

## Slide 5: ST1 ESC Leading Actions (con’t)
Actions:
  Improve/Create High Velocity Learning initiatives targeting the incorporation of Lessons Learned into future availabilities
    ESC Champion: CAPT Dowd (CNSL N43)
  Update front load guidance to expand Amphibious equipment coverage
    ESC Champion: CAPT Johnson (CO SURFMEPP)
  Improve metrics/data analytics capability across entire End-to-End Process
    ESC Champion: CAPT Murray (PMS 443)
  Develop policy message IRT late add, growth and new work gates
    ESC Champion: CAPT Dowd (CNSL N43)/CDR Karosich (CNSP N43)
Actionable Solutions For Immediate Impact To Future Avails

## Slide 6: Way Ahead
  Surface Team One Executive Steering Committee will lead refinement of solutions to issues through Knowledge Sharing Networks
  Progress will be briefed to ST1 Governance Council and Fleet Maintenance Officers through CRCPT and CNSL PB4M2
Actionable Solutions For Immediate Impact To Future Avails

## Slide 8: Data Sources
Review performance using all correspondence and reports utilized in the E2E process to coordinate efforts for planning and executing ship availabilities
    LCPC letter
    Class Maintenance Plans (CMPs)
    Class Standard Work Templates (CSWTs)
    Work Items (WIs)
    Modernization Letters Of Authorization (LOAs)
    A-220 Deferral Letters and response letters
    Baseline Availability Work Package (BAWP) A-360 turnover letters
    IPTD Reports (A-360, A-240, A-145, A-30)
    TYCOM and RMC planning weekly reports and milestone tracker
    Lock Letters, Ready to start letters
    Avail Duration Scorecard F2F reports
    Ship SITREPS, RCCs

## Slide 9
E2E Process Compliance Issues
LLTM - A-360 IPTD: FIRE PUMP REPLACEMENT (S/A 6060) - On TYCOM LOA Sep 2016. Added as new work 10 Oct 17.
LLTM - A-240 IPTD: PM concerned about EP funds for LLTM. Nr.1 Boiler 5 yr SAI
LLTM - A-145 IPTD: NR1 boiler 5 YR SAI
NEW WORK – A-30 – 14 new work items requested by S/F Oct 2017 (Inside A-30)
NEW WORK - WEEK 2 – Yellow – #2/#5 SSTG AND FP S/A 6060. Temp Services 15%
NEW WORK - WEEK 7 – Yellow –. SPS-49 foundation. Nr,1 and Nr.2 Evap
NEW WORK - WEEK 9 – Yellow – 5 tank repairs from FY15 DPMA discovered to not be in the work package.
MANPOWER / RCCs - 41 DAY SLIP OF PCD - WEEK 17 – Red –59 of 65 RCCs settled to support PCD. Boiler work slow. MARMC assessors slow. 10 tanks remain. No blast & painting in tanks has started. MARMC STATED GOAL FOR 50 PERCENT CONFERENCE WAS TO HAVE ALL TANKS ASSESSED
RCCs UPOBS / MANPOWER / LLTM - 57 DAY SLIP TO PCD - WEEK 20 – Red –. 68 jobs behind schedule. No Blast & Painting Started. MRG bearing work not started / Awaiting parts before BAE will start. 22 jobs awaiting material– 1,250 parts / Manning Levels Remain Below Planned Levels.
DURATION DRIVERS:
  MATERIAL–
    YES – RCC Material UPOBS
    YES – LLTM backlog impacted work progress and PCD
  MANPOWER –
    YES – Manpower – Tank assessors
    YES – Contractor manning levels below planned levels
  SA 6060 - SSTG – YES – funded by TYCOM for immature alteration as remedy to Fire Pump repair requirement
USS BATAAN PMA 3-1 11/6/2017 – 10/15/2018 (A+296)

## Slide 10: USS CARTER HALL PMA 3-2 1/22/2018 – 9/24/2018 (A+219)
E2E Process Compliance Issues
MANPOWER – WEEK 11 - OEM TECH REPS: Difficulty to schedule OEM tech assist with concerns highlighted.
LLTM - A+33 - PM indicated a delay in GFM, There were 16 Work Items in “Stop Work” status, Also13 SSDG items parts delivery beyond PCD. MITIGATION decision - 12 MTR’s deferred not adjudicated to allow equipment to remain intact since the material couldn’t be obtained. The MT to re-screened to future CMAVs to maintain schedule.
DURATION - Galley Upgrade the driver for impending Avail Extension due to a new style VCC Cabinet by the Vendor required a foundation mod due to a Vendor Design Change unknown to the Planning Yard. LLTM issues is the cause of late delivery.
DIESEL MAINTENANCE STRATEGY - Work package developed using DMS.
  All DMS deliverable milestones met. ( Avail Impact Report, BAWP review, 100% branding report)
  Comprehensive diesel summary delivered and “Push” tasks sent ISO package lock.
  Branding codes and Due Dates set ICW maintenance team and put in package
  Growth experienced was on items that could NOT be identified earlier
DURATION DRIVERS:
  MATERIAL–
    YES - LLTM - Galley Upgrade the driver for Avail Extension due to a new style VCC Cabinet by the Vendor
    YES – LLTM – SSDG parts difficult to obtain
  PERSONNEL-
    YES – Diesel/Brake repair: OEM unavailable. MARCM Code 220 provided production oversight.

## Slide 11: USS AMERICA PMA 1-1 3/19/2018 – 12/7/2018 (A+163)
E2E Process Compliance Issues
LLTM - SSDG 8K WORK ITEM – 8K hour maintenance SF originated; 18 month assessment DEI is mandatory; WI originated from SF 2Kilos, branded by SURFMEPP, Engines were at approx. 3k hours, 2K requested 009-90 and listed work outside 8k repair requirement (camshafts 32k hour requirement). SF level PMS requirements included in the 2Kilo. PE combined multiple jobs into one work item for each engine to avoid split responsibility and in preparation to impending shift of homeport to Japan.
LLTM – SSDG CAM SHAFT PITTING – Repair Decision timeline Parts avail … Fairbanks Morse? Camshaft was determined to be replaced after casualty (06NOV2017) while ship was deployed. Camshaft was ordered with EDD of 2/20/2019 which is after end of avail.
LLTM - ELEVATORS – ASSESSMENT: 18M situational periodicity condition; 3rd rail, deck edge aircraft; They were accomplished in 2016, 2017 and 2018. Currently have 2 active assessment tasks due in 2019.Assess aircraft elevator IAW NSTM 588 using MRC FY16 for guidance; REPAIR: 144m situational periodicity condition: 3rd rail, ace wire ropes require replacement, replace aircraft elevator wire ropes in accordance with CSWT 588-013
MATERIAL – ELEVATORS - ROLLERS – OEM inspected guide and thrust rollers and found no issue. Rollers will be reused. There is a mod in progress (WI 588-80-001 ACE Grease Line Size Increase (SA-D 82019)). See no issue in accomplishing ACE jobs.
TEMPORARY SERVICES - CHT TANK PRESERVATION and associated system jobs will not meet on time delivery
ASSESSMENTS - OPEN AND INSPECTION and Level II met 20% milestone
DURATION DRIVERS:
  MATERIAL–
    NO- SSDG Camshafts (Over executed requirement) – MITIGATED - AMA received one from new construction about two months ago. Installation/reassembly in progress.
    NO - Elevator Rollers – MITIGATED - OEM decision to reuse old ones
  TEMPORARY SERVICES DELAY –
    YES - CHT Tank preservation and ancillary equipment repair – Letter of Concern - One off issue

## Slide 12: USS BOXER SRA1-1 11/28/2016 – 03/02/2018 (C+180)
PLACE HOLDER
E2E Process Compliance Issues
FUNDING - WEEK 5 - MOISTURE SEPARATORS - Failure To Acquire Funding For Moisture Separators And Begin Shop Fabrication By Mid January Will Impact The PCD Milestone Moist/Sep Pre-fab.
GROWTH - WEEK 26 - SUPPLY VENTILATION PLENUMS – EOA moved to 19JAN 18 In Support Of Repairs To Supply Ventilation Plenums And Trunks. Blast complete on the Original 12 plenums with 4 plenums requiring significant work.
NEW WORK – WEEK 28 - 42 day Extension Request (R 061610Z JUN 16 ZYB) - AUXILIARY MACHINERY SPACE BILGE PRESERVATION.
Request availability completion extension of 42 days
NEW WORK - C+21 IPTD: Avail extension #1 was due to BILGE PRESERVATION added to the package after 100% Lock and prior to start
GROWTH - C+21 IPTD: Avail Extension #2 due to the following:; Tank structural growth work
GROWTH - C+21 IPTD: Avail Extension #2 due to the following: SSTG voltage regulator install
GROWTH - C+21 IPTD: Avail Extension #2 due to the following: M-L Replace Vent Trunk moisture separators
DURATION DRIVERS:
  FUNDING –
    YES - MOISTURE SEPARATOR - Delayed work progress on shop fabrication
  GROWTH –
    YES - SUPPLY VENTILATION PLENUMS & SSTG SCD 11158K - Avail Extension request
  NEW WORK –
    YES - AUXILIARY MACHINERY SPACE BILGE PRESERVATION.- Avail Extension request

## Slide 13: USS SOMERSET SRA1-1 9/18/2017 – 6/1/2019 (C+89)
E2E Process Compliance Issues
EXECUTION - All tanks open for inspection and repair (43 of 43). Setup for preservation is I/P.
PRE AVAIL ASSESSMENTS – Completed on time ISO work package development - G1N6 Completed and closed
DURATION – ADS - Avail duration mitigated to Green – deferred SPS-48G and SSDS
DEFERRALS – No deferrals requested
DURATION DRIVERS:
  YES - NAVAL MESSAGE: AMPN/REF A IS SWRMC TWO WEEK SRA EXTENSION REQUEST ISO SF TRAINING AND CERTIFICATION.// GENTEXT/REMARKS/1. REF A REQUEST APPROVED. 2. SUBJ SRA DATES CHANGED AS FOL:USS SOMERSET (LPD 25) FY17 SRA SSD 18SEP17-01JUN18 VICE 18SEP17-18MAY18
*Avail extension driver in execution: Purifiers (3 Lube Oil Purifiers, 1 Fuel Oil Purifier) were in lay-up throughout execution, and did not work correctly when brought back online due sediment caked in.
- TSRA conducted prior to avail. Results for LOP: "Operational." No assessment noted on FOP.
- Only repair job written: EM02-WG14 - Lube Oil Purifier pressure gage not operational. Not related to issue stated above.
PLACE HOLDER

## Slide 14: Amphibious Ship WG and Way Ahead
O-6 level meeting held 20-21 Sep with representatives from SEA 21, CNRMC, SEA 05, RMCs, TYCOM, ESG, PEO, NAVSUP, MARFORCOM, FFC, INSURV, and SPAWAR
  Review availabilities to identify root causes for avail extensions
  Develop actionable recommendations to improve performance
Planning, Long Lead Time Material (LLTM), Execution, and Growth/New work identified as key challenge areas during avail analysis;
  3PP spec quality, late adds
  No clear material process owner
  Contracting strategy
  Inadequate Integrated Production Schedules (IPS)
  Change management
Key recommendations:
  Targeted assessments on the right equipment at the right time
  Develop a Bilge Phasing Plan (similar to tanks) to systematically level load bilge work
  Establish ST1 Material Knowledge Sharing Network (KSN)/Material Process Team to improve material process and bring in major players
  Improve feedback loop for Avail Duration Scorecard (ADS)
  Update front load guidance to cover more of the operationally vital Amphibious equipment
  Enhance process for new work induction that will identify risks to avail duration earlier and properly account for and communicate those risks to operational schedules
  Reinvigorate Lessons Learned (LL) process targeting the incorporation of LL into future availabilities;
  Improve metrics/data analytics capability across entire End-to-End Process
  3 Star (COMNAVSEA, COMNAVSURFOR) out-brief scheduled during Maintenance and Modernization (MM) Summit 24OCT
Stakeholders teaming to improve Amphibious Ship availability