## Cover
Domestic Private Sector Workload Estimate
“This information is to provide U.S. DoD industry contractors a general schedule (for information and planning purposes only) for upcoming surface ship maintenance periods - It does not constitute any request for information or request for proposals, nor is it a commitment to contract for work in accordance with this plan. This information is provided to U.S. DoD industry contractors to give a broad overview of frequently changing (driven by U.S. Navy operations) maintenance schedules and is not a guarantee of exact workload or ship schedules”
CMAV Workload FY25 Q1 – FY25 Q4 as of 02 OCTOBER 2024
Industry Version
“Distribution Statement A: Approved for Public Release; Distribution is unlimited.”

## Notes
Data contained in this report reflects the Navy program of record as of 02 OCTOBER 2024.
This report is provided to our CONUS industry partners for information and planning purposes only. The information provided reflects a broad overview of current maintenance schedules and is subject to change based on operational commitments. It does not constitute a request for information or proposals, nor is it a commitment to contract work in accordance with this plan.
The next bi-monthly CMAV workload projections are targeted for release no later than 31 DECEMBER 2024.
Availability duration and schedule review, tailored acquisition strategies and ongoing budget negotiations may refine out-year projections.
“Distribution Statement A: Approved for Public Release; Distribution is unlimited.”
“This information is to provide U.S. DoD industry contractors a general schedule (for information and planning purposes only) for upcoming surface ship maintenance periods - It does not constitute any request for information or request for proposals, nor is it a commitment to contract for work in accordance with this plan. This information is provided to U.S. DoD industry contractors to give a broad overview of frequently changing (driven by U.S. Navy operations) maintenance schedules and is not a guarantee of exact workload or ship schedules”

## MARMC
Hull | Ship | Homeport | Event | Status | Start Date | End Date | Duration (D)
LSD 46 | TORTUGA | Little Creek | CMAV (A) | ACTIVE | 2023-11-20 | 2025-02-28 | 467
DDG 72 | MAHAN | Norfolk | CMAV (A) | ACTIVE | 2024-08-26 | 2024-10-03 | 39
DDG 98 | FORREST SHERMAN | Norfolk | CMAV (A) | ACTIVE | 2024-09-03 | 2024-10-04 | 32
LPD 28 | FORT LAUDERDALE | Norfolk | CMAV (A) | ACTIVE | 2024-09-03 | 2024-10-18 | 46
DDG 58 | LABOON | Norfolk | CMAV (A) | ACTIVE | 2024-09-09 | 2024-10-25 | 47
DDG 78 | PORTER | Norfolk | CMAV (A) | ACTIVE | 2024-09-30 | 2024-11-13 | 45
DDG 71 | ROSS | Norfolk | CMAV (A) | ACTIVE | 2024-10-21 | 2024-11-29 | 40
LPD 24 | ARLINGTON | Norfolk | CMAV (A) | ACTIVE | 2024-10-28 | 2024-12-06 | 40
CG 60 | NORMANDY | Norfolk | CMAV (A) | ACTIVE | 2024-11-12 | 2025-01-10 | 60
CG 58 | PHILIPPINE SEA | Norfolk | CMAV (A) | ACTIVE | 2024-12-02 | 2025-01-24 | 54
DDG 72 | MAHAN | Norfolk | CMAV (A) | ACTIVE | 2024-12-02 | 2025-01-31 | 61
DDG 58 | LABOON | Norfolk | CMAV (A) | ACTIVE | 2024-12-02 | 2025-02-09 | 70
LSD 51 | OAK HILL | Little Creek | CMAV (A) | ACTIVE | 2024-12-09 | 2025-01-31 | 54
LHD 1 | WASP | Norfolk | CMAV (A) | ACTIVE | 2024-12-09 | 2025-01-17 | 40
LHD 7 | IWO JIMA | Norfolk | CMAV (A) | ACTIVE | 2024-12-09 | 2025-01-24 | 47
LPD 28 | FORT LAUDERDALE | Norfolk | CMAV (A) | ACTIVE | 2024-12-09 | 2025-02-07 | 61
LPD 21 | NEW YORK | Norfolk | CMAV (A) | ACTIVE | 2024-12-09 | 2025-02-14 | 68
LSD 44 | GUNSTON HALL | Little Creek | CMAV (A) | ACTIVE | 2024-12-16 | 2025-03-21 | 96
LPD 17 | SAN ANTONIO | Norfolk | CMAV (A) | ACTIVE | 2024-12-16 | 2025-01-24 | 40
DDG 96 | BAINBRIDGE | Norfolk | CMAV (A) | ACTIVE | 2024-12-16 | 2025-01-31 | 47
DDG 98 | FORREST SHERMAN | Norfolk | CMAV (A) | ACTIVE | 2024-12-16 | 2025-01-31 | 47
DDG 74 | MCFAUL | Norfolk | CMAV (A) | ACTIVE | 2024-12-16 | 2025-02-07 | 54
DDG 78 | PORTER | Norfolk | CMAV (A) | ACTIVE | 2025-01-06 | 2025-02-14 | 40
DDG 57 | MITSCHER | Norfolk | CMAV (A) | ACTIVE | 2025-01-06 | 2025-02-14 | 40
LHD 3 | KEARSARGE | Norfolk | CMAV (A) | ACTIVE | 2025-01-06 | 2025-02-14 | 40
DDG 107 | GRAVELY | Norfolk | CMAV (A) | ACTIVE | 2025-01-27 | 2025-03-07 | 40
DDG 67 | COLE | Norfolk | CMAV (A) | ACTIVE | 2025-02-18 | 2025-04-04 | 46
DDG 78 | PORTER | Norfolk | CMAV (A) | ACTIVE | 2025-03-24 | 2025-05-04 | 42
LPD 24 | ARLINGTON | Norfolk | CMAV (A) | ACTIVE | 2025-03-31 | 2025-04-18 | 19
DDG 66 | GONZALEZ | Norfolk | CMAV (A) | ACTIVE | 2025-04-07 | 2025-04-25 | 19
DDG 71 | ROSS | Norfolk | CMAV (A) | ACTIVE | 2025-04-07 | 2025-04-25 | 19
LHD 7 | IWO JIMA | Norfolk | CMAV (A) | ACTIVE | 2025-04-14 | 2025-05-09 | 26
LPD 17 | SAN ANTONIO | Norfolk | CMAV (A) | ACTIVE | 2025-04-14 | 2025-05-09 | 26
LPD 28 | FORT LAUDERDALE | Norfolk | CMAV (A) | ACTIVE | 2025-04-14 | 2025-05-09 | 26
DDG 55 | STOUT | Norfolk | CMAV (A) | ACTIVE | 2025-04-21 | 2025-05-16 | 26
DDG 57 | MITSCHER | Norfolk | CMAV (A) | ACTIVE | 2025-04-21 | 2025-06-06 | 47
DDG 96 | BAINBRIDGE | Norfolk | CMAV (A) | ACTIVE | 2025-04-28 | 2025-06-20 | 54
DDG 72 | MAHAN | Norfolk | CMAV (A) | ACTIVE | 2025-05-05 | 2025-06-13 | 40
CG 58 | PHILIPPINE SEA | Norfolk | CMAV (A) | ACTIVE | 2025-05-19 | 2025-09-25 | 130
CG 64 | GETTYSBURG | Norfolk | CMAV (A) | ACTIVE | 2025-05-27 | 2025-09-25 | 122
CG 60 | NORMANDY | Norfolk | CMAV (A) | ACTIVE | 2025-05-27 | 2025-09-25 | 122
DDG 94 | NITZE | Norfolk | CMAV (A) | ACTIVE | 2025-06-09 | 2025-07-18 | 40
LSD 51 | OAK HILL | Little Creek | CMAV (A) | ACTIVE | 2025-07-14 | 2025-08-24 | 42
DDG 55 | STOUT | Norfolk | CMAV (A) | ACTIVE | 2025-07-14 | 2025-08-22 | 40
LHD 7 | IWO JIMA | Norfolk | CMAV (A) | ACTIVE | 2025-07-15 | 2025-08-12 | 29
LPD 17 | SAN ANTONIO | Norfolk | CMAV (A) | ACTIVE | 2025-07-15 | 2025-08-12 | 29
LPD 28 | FORT LAUDERDALE | Norfolk | CMAV (A) | ACTIVE | 2025-07-15 | 2025-08-12 | 29
LSD 44 | GUNSTON HALL | Little Creek | CMAV (A) | ACTIVE | 2025-07-21 | 2025-08-29 | 40
DDG 74 | MCFAUL | Norfolk | CMAV (A) | ACTIVE | 2025-07-21 | 2025-08-22 | 33
LPD 21 | NEW YORK | Norfolk | CMAV (A) | ACTIVE | 2025-07-21 | 2025-08-31 | 42
LHD 3 | KEARSARGE | Norfolk | CMAV (A) | ACTIVE | 2025-07-28 | 2025-09-05 | 40
DDG 71 | ROSS | Norfolk | CMAV (A) | ACTIVE | 2025-08-04 | 2025-09-12 | 40
DDG 66 | GONZALEZ | Norfolk | CMAV (A) | ACTIVE | 2025-08-04 | 2025-09-12 | 40
DDG 103 | TRUXTUN | Norfolk | CMAV (A) | ACTIVE | 2025-08-11 | 2025-09-19 | 40
LPD 24 | ARLINGTON | Norfolk | CMAV (A) | ACTIVE | 2025-08-11 | 2025-09-19 | 40
DDG 67 | COLE | Norfolk | CMAV (A) | ACTIVE | 2025-09-02 | 2025-09-28 | 27
“Distribution Statement A: Approved for Public Release; Distribution is unlimited.”
“This information is to provide U.S. DoD industry contractors a general schedule (for information and planning purposes only) for upcoming surface ship maintenance periods - It does not constitute any request for information or request for proposals, nor is it a commitment to contract for work in accordance with this plan. This information is provided to U.S. DoD industry contractors to give a broad overview of frequently changing (driven by U.S. Navy operations) maintenance schedules and is not a guarantee of exact workload or ship schedules”

## SERMC
Hull | Ship | Homeport | Event | Status | Start Date | End Date | Duration (D)
LCS 23 | COOPERSTOWN | Mayport | CMAV (A) | ACTIVE | 2024-02-05 | 2024-12-07 | 307
LCS 15 | BILLINGS | Mayport | CMAV (A) | ACTIVE | 2024-08-05 | 2024-11-08 | 96
DDG 81 | WINSTON S CHURCHILL | Mayport | CMAV (A) | ACTIVE | 2024-08-19 | 2024-10-04 | 47
DDG 75 | DONALD COOK | Mayport | CMAV (A) | ACTIVE | 2024-08-26 | 2024-10-04 | 40
DDG 68 | THE SULLIVANS | Mayport | CMAV (A) | ACTIVE | 2024-08-28 | 2024-10-20 | 54
LCS 13 | WICHITA | Mayport | CMAV (A) | ACTIVE | 2024-09-09 | 2024-10-25 | 47
DDG 82 | LASSEN | Mayport | CMAV (A) | ACTIVE | 2024-10-07 | 2025-01-10 | 96
LCS 25 | MARINETTE | Mayport | CMAV (A) | ACTIVE | 2024-10-14 | 2025-02-28 | 138
LCS 15 | BILLINGS | Mayport | CMAV (A) | ACTIVE | 2024-11-12 | 2024-12-20 | 39
DDG 116 | THOMAS HUDNER | Mayport | CMAV (A) | ACTIVE | 2024-11-18 | 2025-01-10 | 54
LCS 21 | MINNEAPOLIS-SAINT PAUL | Mayport | CMAV (A) | ACTIVE | 2024-12-02 | 2025-01-10 | 40
LCS 27 | NANTUCKET | Mayport | CMAV (A) | ACTIVE | 2024-12-09 | 2025-01-17 | 40
DDG 75 | DONALD COOK | Mayport | CMAV (A) | ACTIVE | 2024-12-16 | 2025-01-31 | 47
DDG 81 | WINSTON S CHURCHILL | Mayport | CMAV (A) | ACTIVE | 2024-12-16 | 2025-01-31 | 47
LCS 17 | INDIANAPOLIS | Mayport | CMAV (A) | ACTIVE | 2025-01-06 | 2025-02-14 | 40
LCS 23 | COOPERSTOWN | Mayport | CMAV (A) | ACTIVE | 2025-01-06 | 2025-02-14 | 40
DDG 99 | FARRAGUT | Mayport | CMAV (A) | ACTIVE | 2025-01-21 | 2025-02-28 | 39
LCS 29 | BELOIT | Mayport | CMAV (A) | ACTIVE | 2025-02-10 | 2025-03-28 | 47
LCS 25 | MARINETTE | Mayport | CMAV (A) | ACTIVE | 2025-03-03 | 2025-04-11 | 40
DDG 119 | DELBERT D BLACK | Mayport | CMAV (A) | ACTIVE | 2025-03-31 | 2025-05-02 | 33
DDG 75 | DONALD COOK | Mayport | CMAV (A) | ACTIVE | 2025-04-07 | 2025-04-25 | 19
LCS 15 | BILLINGS | Mayport | CMAV (A) | ACTIVE | 2025-04-14 | 2025-05-02 | 19
DDG 82 | LASSEN | Mayport | CMAV (A) | ACTIVE | 2025-04-14 | 2025-05-09 | 26
LCS 19 | ST LOUIS | Mayport | CMAV (A) | ACTIVE | 2025-04-14 | 2025-05-30 | 47
DDG 109 | JASON DUNHAM | Mayport | CMAV (A) | ACTIVE | 2025-04-21 | 2025-05-30 | 40
DDG 64 | CARNEY | Mayport | CMAV (A) | ACTIVE | 2025-05-05 | 2025-06-13 | 40
DDG 81 | WINSTON S CHURCHILL | Mayport | CMAV (A) | ACTIVE | 2025-05-05 | 2025-06-20 | 47
LCS 13 | WICHITA | Mayport | CMAV (A) | ACTIVE | 2025-05-12 | 2025-06-20 | 40
DDG 68 | THE SULLIVANS | Mayport | CMAV (A) | ACTIVE | 2025-06-23 | 2025-08-01 | 40
LCS 27 | NANTUCKET | Mayport | CMAV (A) | ACTIVE | 2025-07-01 | 2025-10-31 | 123
DDG 116 | THOMAS HUDNER | Mayport | CMAV (A) | ACTIVE | 2025-07-07 | 2025-08-15 | 40
DDG 119 | DELBERT D BLACK | Mayport | CMAV (A) | ACTIVE | 2025-07-07 | 2025-08-15 | 40
DDG 87 | MASON | Mayport | CMAV (A) | ACTIVE | 2025-07-07 | 2025-08-15 | 40
LCS 15 | BILLINGS | Mayport | CMAV (A) | ACTIVE | 2025-07-14 | 2025-08-22 | 40
DDG 75 | DONALD COOK | Mayport | CMAV (A) | ACTIVE | 2025-08-04 | 2025-09-12 | 40
DDG 68 | THE SULLIVANS | Mayport | CMAV (A) | ACTIVE | 2025-08-18 | 2025-09-28 | 42
LCS 29 | BELOIT | Mayport | CMAV (A) | ACTIVE | 2025-09-01 | 2025-11-30 | 91
DDG 61 | RAMAGE | Mayport | CMAV (A) | ACTIVE | 2025-09-02 | 2025-10-10 | 39
DDG 99 | FARRAGUT | Mayport | CMAV (A) | ACTIVE | 2025-09-08 | 2025-10-17 | 40
DDG 64 | CARNEY | Mayport | CMAV (A) | ACTIVE | 2025-09-15 | 2025-10-17 | 33
DDG 82 | LASSEN | Mayport | CMAV (A) | ACTIVE | 2025-09-22 | 2025-10-31 | 40
“Distribution Statement A: Approved for Public Release; Distribution is unlimited.”
“This information is to provide U.S. DoD industry contractors a general schedule (for information and planning purposes only) for upcoming surface ship maintenance periods - It does not constitute any request for information or request for proposals, nor is it a commitment to contract for work in accordance with this plan. This information is provided to U.S. DoD industry contractors to give a broad overview of frequently changing (driven by U.S. Navy operations) maintenance schedules and is not a guarantee of exact workload or ship schedules”

## SWRMC
Hull | Ship | Homeport | Event | Status | Start Date | End Date | Duration (D)
LCS 3 | FORT WORTH | San Diego | CMAV (A) | ACTIVE | 2024-08-19 | 2025-01-05 | 140
DDG 89 | MUSTIN | San Diego | CMAV (A) | ACTIVE | 2024-08-26 | 2024-10-04 | 40
CG 59 | PRINCETON | San Diego | CMAV (A) | ACTIVE | 2024-08-26 | 2024-10-04 | 40
LPD 27 | PORTLAND | San Diego | CMAV (A) | ACTIVE | 2024-08-26 | 2024-10-18 | 54
LSD 45 | COMSTOCK | San Diego | CMAV (A) | ACTIVE | 2024-10-14 | 2024-11-25 | 43
LCS 22 | KANSAS CITY | San Diego | CMAV (A) | ACTIVE | 2024-10-15 | 2024-11-22 | 39
LCS 14 | MANCHESTER | San Diego | CMAV (A) | ACTIVE | 2024-10-17 | 2024-11-29 | 44
LCS 18 | CHARLESTON | San Diego | CMAV (A) | ACTIVE | 2024-10-21 | 2024-12-13 | 54
DDG 54 | CURTIS WILBUR | San Diego | CMAV (A) | ACTIVE | 2024-10-28 | 2024-12-06 | 40
DDG 123 | LENAH H SUTCLIFFE HIGBEE | San Diego | CMAV (A) | ACTIVE | 2024-11-04 | 2024-12-15 | 42
CG 65 | CHOSIN | San Diego | CMAV (A) | ACTIVE | 2024-11-12 | 2024-12-31 | 50
LSD 48 | ASHLAND | San Diego | CMAV (A) | ACTIVE | 2024-11-18 | 2025-01-17 | 61
LSD 42 | GERMANTOWN | San Diego | CMAV (A) | ACTIVE | 2024-11-18 | 2025-02-25 | 100
LCS 30 | CANBERRA | San Diego | CMAV (A) | ACTIVE | 2024-11-25 | 2025-01-07 | 44
LHD 4 | BOXER | San Diego | CMAV (A) | ACTIVE | 2024-12-02 | 2025-01-03 | 33
DDG 62 | FITZGERALD | San Diego | CMAV (A) | ACTIVE | 2024-12-02 | 2025-01-10 | 40
DDG 59 | RUSSELL | San Diego | CMAV (A) | ACTIVE | 2024-12-02 | 2025-01-17 | 47
LCS 20 | CINCINNATI | San Diego | CMAV (A) | ACTIVE | 2024-12-05 | 2025-01-05 | 32
DDG 90 | CHAFEE | San Diego | CMAV (A) | ACTIVE | 2024-12-06 | 2025-01-31 | 57
LCS 16 | TULSA | San Diego | CMAV (A) | ACTIVE | 2024-12-09 | 2025-01-17 | 40
LHD 2 | ESSEX | San Diego | CMAV (A) | ACTIVE | 2024-12-09 | 2025-01-17 | 40
LCS 6 | JACKSON | San Diego | CMAV (A) | ACTIVE | 2024-12-09 | 2025-01-24 | 47
LCS 32 | SANTA BARBARA | San Diego | CMAV (A) | ACTIVE | 2024-12-16 | 2025-01-17 | 33
DDG 111 | SPRUANCE | San Diego | CMAV (A) | ACTIVE | 2024-12-16 | 2025-01-24 | 40
LCS 8 | MONTGOMERY | San Diego | CMAV (A) | ACTIVE | 2024-12-16 | 2025-02-11 | 58
LCS 24 | OAKLAND | San Diego | CMAV (A) | ACTIVE | 2024-12-23 | 2025-01-30 | 39
LSD 45 | COMSTOCK | San Diego | CMAV (A) | ACTIVE | 2024-12-30 | 2025-02-14 | 47
DDG 89 | MUSTIN | San Diego | CMAV (A) | ACTIVE | 2025-01-02 | 2025-02-13 | 43
LCS 3 | FORT WORTH | San Diego | CMAV (A) | ACTIVE | 2025-01-06 | 2025-02-14 | 40
LHA 7 | TRIPOLI | San Diego | CMAV (A) | ACTIVE | 2025-01-06 | 2025-03-21 | 75
LSD 49 | HARPERS FERRY | San Diego | CMAV (A) | ACTIVE | 2025-01-08 | 2025-02-28 | 52
LPD 23 | ANCHORAGE | San Diego | CMAV (A) | ACTIVE | 2025-01-13 | 2025-02-21 | 40
LPD 25 | SOMERSET | San Diego | CMAV (A) | ACTIVE | 2025-01-13 | 2025-02-21 | 40
LSD 52 | PEARL HARBOR | San Diego | CMAV (A) | ACTIVE | 2025-01-13 | 2025-03-10 | 57
DDG 91 | PINCKNEY | San Diego | CMAV (A) | ACTIVE | 2025-01-17 | 2025-02-27 | 42
CG 70 | LAKE ERIE | San Diego | CMAV (A) | ACTIVE | 2025-01-31 | 2025-03-13 | 42
DDG 77 | OKANE | San Diego | CMAV (A) | ACTIVE | 2025-02-08 | 2025-03-06 | 27
LCS 22 | KANSAS CITY | San Diego | CMAV (A) | ACTIVE | 2025-02-18 | 2025-03-28 | 39
LPD 26 | JOHN P MURTHA | San Diego | CMAV (A) | ACTIVE | 2025-02-18 | 2025-04-04 | 46
DDG 62 | FITZGERALD | San Diego | CMAV (A) | ACTIVE | 2025-02-18 | 2025-04-11 | 53
DDG 123 | LENAH H SUTCLIFFE HIGBEE | San Diego | CMAV (A) | ACTIVE | 2025-02-24 | 2025-03-16 | 21
LCS 10 | GABRIELLE GIFFORDS | San Diego | CMAV (A) | ACTIVE | 2025-02-24 | 2025-03-21 | 26
DDG 106 | STOCKDALE | San Diego | CMAV (A) | ACTIVE | 2025-02-24 | 2025-04-04 | 40
DDG 59 | RUSSELL | San Diego | CMAV (A) | ACTIVE | 2025-03-10 | 2025-03-30 | 21
LCS 14 | MANCHESTER | San Diego | CMAV (A) | ACTIVE | 2025-03-10 | 2025-04-13 | 35
LHD 4 | BOXER | San Diego | CMAV (A) | ACTIVE | 2025-03-24 | 2025-04-13 | 21
LHD 8 | MAKIN ISLAND | San Diego | CMAV (A) | ACTIVE | 2025-03-24 | 2025-05-23 | 61
DDG 77 | OKANE | San Diego | CMAV (A) | ACTIVE | 2025-03-31 | 2025-05-02 | 33
LHD 2 | ESSEX | San Diego | CMAV (A) | ACTIVE | 2025-03-31 | 2025-05-09 | 40
DDG 60 | PAUL HAMILTON | San Diego | CMAV (A) | ACTIVE | 2025-03-31 | 2025-05-09 | 40
DDG 63 | STETHEM | San Diego | CMAV (A) | ACTIVE | 2025-03-31 | 2025-05-23 | 54
LCS 34 | AUGUSTA | San Diego | CMAV (A) | ACTIVE | 2025-04-14 | 2025-05-23 | 40
LCS 18 | CHARLESTON | San Diego | CMAV (A) | ACTIVE | 2025-04-14 | 2025-05-23 | 40
CG 59 | PRINCETON | San Diego | CMAV (A) | ACTIVE | 2025-04-28 | 2025-06-06 | 40
LCS 20 | CINCINNATI | San Diego | CMAV (A) | ACTIVE | 2025-05-05 | 2025-06-13 | 40
LCS 6 | JACKSON | San Diego | CMAV (A) | ACTIVE | 2025-05-19 | 2025-12-19 | 215
LCS 8 | MONTGOMERY | San Diego | CMAV (A) | ACTIVE | 2025-05-19 | 2025-12-19 | 215
DDG 77 | OKANE | San Diego | CMAV (A) | ACTIVE | 2025-06-02 | 2025-06-30 | 29
DDG 111 | SPRUANCE | San Diego | CMAV (A) | ACTIVE | 2025-06-02 | 2025-07-11 | 40
DDG 106 | STOCKDALE | San Diego | CMAV (A) | ACTIVE | 2025-06-16 | 2025-07-18 | 33
DDG 104 | STERETT | San Diego | CMAV (A) | ACTIVE | 2025-06-30 | 2025-07-20 | 21
DDG 89 | MUSTIN | San Diego | CMAV (A) | ACTIVE | 2025-08-11 | 2025-09-19 | 40
LCS 24 | OAKLAND | San Diego | CMAV (A) | ACTIVE | 2025-08-25 | 2025-10-05 | 42
DDG 91 | PINCKNEY | San Diego | CMAV (A) | ACTIVE | 2025-08-29 | 2025-10-17 | 50
LCS 22 | KANSAS CITY | San Diego | CMAV (A) | ACTIVE | 2025-09-01 | 2025-11-21 | 82
LCS 36 | KINGSVILLE | San Diego | CMAV (A) | ACTIVE | 2025-09-04 | 2025-09-30 | 27
CG 65 | CHOSIN | San Diego | CMAV (A) | ACTIVE | 2025-09-08 | 2025-10-17 | 40
DDG 60 | PAUL HAMILTON | San Diego | CMAV (A) | ACTIVE | 2025-09-08 | 2025-10-17 | 40
LPD 23 | ANCHORAGE | San Diego | CMAV (A) | ACTIVE | 2025-09-08 | 2025-10-17 | 40
DDG 111 | SPRUANCE | San Diego | CMAV (A) | ACTIVE | 2025-09-11 | 2025-10-10 | 30
DDG 106 | STOCKDALE | San Diego | CMAV (A) | ACTIVE | 2025-09-15 | 2025-10-17 | 33
LCS 3 | FORT WORTH | San Diego | CMAV (A) | ACTIVE | 2025-09-15 | 2025-10-24 | 40
LCS 34 | AUGUSTA | San Diego | CMAV (A) | ACTIVE | 2025-09-22 | 2025-10-31 | 40
“Distribution Statement A: Approved for Public Release; Distribution is unlimited.”
“This information is to provide U.S. DoD industry contractors a general schedule (for information and planning purposes only) for upcoming surface ship maintenance periods - It does not constitute any request for information or request for proposals, nor is it a commitment to contract for work in accordance with this plan. This information is provided to U.S. DoD industry contractors to give a broad overview of frequently changing (driven by U.S. Navy operations) maintenance schedules and is not a guarantee of exact workload or ship schedules”

## NWRMC
Hull | Ship | Homeport | Event | Status | Start Date | End Date | Duration (D)
DDG 56 | JOHN S MCCAIN | Everett | CMAV (A) | ACTIVE | 2024-10-21 | 2024-11-15 | 26
DDG 101 | GRIDLEY | Everett | CMAV (A) | ACTIVE | 2024-10-21 | 2024-11-29 | 40
DDG 53 | JOHN PAUL JONES | Everett | CMAV (A) | ACTIVE | 2024-11-12 | 2024-12-20 | 39
DDG 102 | SAMPSON | Everett | CMAV (A) | ACTIVE | 2024-11-19 | 2024-12-31 | 43
DDG 100 | KIDD | Everett | CMAV (A) | ACTIVE | 2024-11-25 | 2025-01-05 | 42
DDG 56 | JOHN S MCCAIN | Everett | CMAV (A) | ACTIVE | 2025-01-06 | 2025-01-31 | 26
CG 71 | CAPE ST GEORGE | Everett | CMAV (A) | ACTIVE | 2025-01-22 | 2025-04-08 | 77
DDG 101 | GRIDLEY | Everett | CMAV (A) | ACTIVE | 2025-02-24 | 2025-03-21 | 26
DDG 53 | JOHN PAUL JONES | Everett | CMAV (A) | ACTIVE | 2025-04-14 | 2025-05-29 | 46
“Distribution Statement A: Approved for Public Release; Distribution is unlimited.”
“This information is to provide U.S. DoD industry contractors a general schedule (for information and planning purposes only) for upcoming surface ship maintenance periods - It does not constitute any request for information or request for proposals, nor is it a commitment to contract for work in accordance with this plan. This information is provided to U.S. DoD industry contractors to give a broad overview of frequently changing (driven by U.S. Navy operations) maintenance schedules and is not a guarantee of exact workload or ship schedules”

## HRMC
Hull | Ship | Homeport | Event | Status | Start Date | End Date | Duration (D)
DDG 110 | WILLIAM P LAWRENCE | Pearl Harbor | CMAV (A) | ACTIVE | 2024-09-30 | 2024-11-08 | 40
CG 67 | SHILOH | Pearl Harbor | CMAV (A) | ACTIVE | 2024-10-19 | 2025-01-10 | 84
DDG 118 | DANIEL INOUYE | Pearl Harbor | CMAV (A) | ACTIVE | 2024-10-21 | 2024-12-02 | 43
DDG 108 | WAYNE E MEYER | Pearl Harbor | CMAV (A) | ACTIVE | 2024-11-12 | 2024-12-20 | 39
DDG 112 | MICHAEL MURPHY | Pearl Harbor | CMAV (A) | ACTIVE | 2024-12-16 | 2025-01-24 | 40
DDG 121 | FRANK E PETERSEN JR | Pearl Harbor | CMAV (A) | ACTIVE | 2024-12-16 | 2025-01-24 | 40
DDG 120 | CARL M LEVIN | Pearl Harbor | CMAV (A) | ACTIVE | 2025-02-18 | 2025-04-11 | 53
DDG 118 | DANIEL INOUYE | Pearl Harbor | CMAV (A) | ACTIVE | 2025-02-24 | 2025-03-14 | 19
DDG 108 | WAYNE E MEYER | Pearl Harbor | CMAV (A) | ACTIVE | 2025-02-24 | 2025-04-04 | 40
DDG 73 | DECATUR | Honolulu | CMAV (A) | ACTIVE | 2025-03-17 | 2025-04-18 | 33
DDG 73 | DECATUR | Honolulu | CMAV (A) | ACTIVE | 2025-05-26 | 2025-06-20 | 26
DDG 121 | FRANK E PETERSEN JR | Pearl Harbor | CMAV (A) | ACTIVE | 2025-06-09 | 2025-07-18 | 40
DDG 112 | MICHAEL MURPHY | Pearl Harbor | CMAV (A) | ACTIVE | 2025-06-16 | 2025-07-25 | 40
DDG 120 | CARL M LEVIN | Pearl Harbor | CMAV (A) | ACTIVE | 2025-08-11 | 2025-09-05 | 26
DDG 70 | HOPPER | Pearl Harbor | CMAV (A) | ACTIVE | 2025-08-11 | 2025-09-19 | 40
DDG 108 | WAYNE E MEYER | Pearl Harbor | CMAV (A) | ACTIVE | 2025-08-18 | 2025-09-26 | 40
“Distribution Statement A: Approved for Public Release; Distribution is unlimited.”
“This information is to provide U.S. DoD industry contractors a general schedule (for information and planning purposes only) for upcoming surface ship maintenance periods - It does not constitute any request for information or request for proposals, nor is it a commitment to contract for work in accordance with this plan. This information is provided to U.S. DoD industry contractors to give a broad overview of frequently changing (driven by U.S. Navy operations) maintenance schedules and is not a guarantee of exact workload or ship schedules”